**Financial Bid**

**INDIVIDUAL CONSULTANT FOR C4D Media Based Innovations**

|  |  |  |
| --- | --- | --- |
| **Deliverable (s)** | **UNICEF Estimate** | **Consultant's Proposal** |
| **Estimated deadline for completion of deliverable (please mention as days/months)** | **Estimated travel required for completion of deliverable (please mention destination/ number of days)** | **Complete timeframe for deliverable** | **Cost (INR)**Professional Fee***Please indicate your professional fee only.*** |
| * Partnership agreement with IBF finalized
* Message guidance grid for AdhaFULL Season 2 finalized
 | May 2017  | No travel  |  |  |
| * IPC toolkit components successfully pretested, produced and finalized.
* 8 language adaptations of the IPC kit completed and ready for use in respective states.
* Episode (Ep) 1-10 AF season 2 - approved stories, episodic synopsis, scripts
 | June 2017 | No travel  |  |  |
| * Report on Field and observation visits to UNICEF supported states
* Ep 11-20 AF season 2 - approved the stories, episodic synopsis, scripts
 | July 2017  | 2-3 visits (2-3) days to the states implementing IPC toolkit 2-3 visits (2 days each) to the production studio/locations during Season 2 production One visit (2 days ) to NABM training 1-2 visits (2 days ) for IBF workshop  |  |  |
| * Report on Field and observation visits to UNICEF supported states
* Ep 21-30 AF season 2 - approved the stories, episodic synopsis, scripts
* Ep 1-9 episodes submitted to DD/any other C&S channel
* Report of coordination for broadcast of Full On Nikki on CR stations, AIR/BIG FM
 | August 2017 |  |  |
| * Report on Field and observation visits to UNICEF supported states
* Ep 31-40 AF season 2 - approved the stories, episodic synopsis, scripts
* Ep 10-19 episodes submitted to DD/any other C&S channel
* Content analysis research completed and design of workshop finalized
 | September 2017 |  |  |
| * Ep 41-50 Ep 21-30 AF season 2 - approved the stories, episodic synopsis, scripts
* 20-29 episodes submitted to DD/any other C&S channel and report of coordination with CR, AIR/BIG FM
 | October 2017 |  |  |
| * Ep 51-60 Ep 21-30 AF season 2 - approved the stories, episodic synopsis, scripts
* 30-39 episodes submitted to DD/any other C&S channel and report of coordination with CR, AIR/BIG FM
* Design of NABM workshop finalized and report of workshop submitted
 | November 2017 |  |  |
| * Ep 61-70 Ep 21-30 AF season 2 - approved the stories, episodic synopsis, scripts
* 40-49 episodes submitted to DD/any other C&S channel and report of coordination with CR, AIR/BIG FM
 | December 2017 |  |  |
| * Ep 71-78 AF season 2 - approved the stories, episodic synopsis, scripts
* 50-59 episodes submitted to DD/any other C&S channel and report of coordination with CR, AIR/BIG FM
 | January 2018 |  |  |
| * 60-69 episodes submitted to DD/any other C&S channel and report of coordination with CR, AIR/BIG FM
 | February 2018 |  |  |
| * 70-78 episodes submitted to DD/any other C&S channel and report of coordination with CR, AIR/BIG FM
 | March 2018 |  |  |
| * Report of the IBF partnership/dissemination workshop
* NABM/DD workshop report submitted
 | April 2018 |  |  |

*Shaded area to be filled in by consultant- professional fees for each deliverable to be quoted*

Note: Travel as required/agreed with the Supervisor will be reimbursed on actuals on receipt of a travel claim with supporting documents and invoices.

Per Diem will be reimbursed at UNICEF ICO consultant rates

The consultant is required to make own arrangements for travel and stay

Payment will be made against receipt and acceptance of deliverables.

**Name of the Bidder:**

**Address:**

**Contact no.:**

**Email address:**

**Date :**