|  |  |
| --- | --- |
| **Activity** | **2021 - 2021** |
|  | **Aug** | **Sep** | **Oct** | **Nov** | **Dec** | **Jan** | **Feb** |
| TOR finalised | X |  |  |  |  |  |  |
| Desk review, initial briefs with UNICEF and discussions around existing data, proposals for different ways of data collection (by respondent groups)  | X | X | x |  |  |  |  |
| Inception mission (remote)  |  |  | X |  |  |  |  |
| Inception report |  |  | X |  |  |  |  |
| Report reviewed by evaluation stakeholders, ethical review and quality assurance conducted |  |  | X |  |  |  |  |
| Finalization and approval of Inception Report |  |  | x |  |  |  |  |
| Remote data collection and presentation of preliminary observations and findings |  |  |  | x | x |  |  |
| First draft report |  |  |  |  | x |  |  |
| Report reviewed by evaluation stakeholders, ethical review and quality assurance conducted |  |  |  |  | x |  |  |
| Final Report |  |  |  |  | x | x |  |
| Final presentations |  |  |  |  |  | x | x |
| Management Response (UNICEF)  |  |  |  |  |  |  | x |