|  |  |  |
| --- | --- | --- |
| **Tasks/Milestone:** | **Deliverables/Outputs:** | **Timeline** |
| 1. Provision of methodological support to ECI services in the form of monthly meetings  | 24 reports with topics discussed and recommendations for improvements based on meetings with the ECI teams (4 in Nova Zagora and 4 in Haskovo). | December 2025 (monthly) |
| 2. Review of the methodological guidelines for GPs and other medical practitioners  | Methodological guidelines for GPs for systematic developmental monitoring and screening of young children finalized and disseminated  | March 2024 |
| 3. Review and adapt regional ECD learning platform materials.  | Basic package of ECD online training materials (25 modules) translated, validated and adapted for the Bulgarian context | December 2024 (min 2 modules each month) |
| 4. Development of additional content of materials for ECD practitioners.  | Additional package of materials (20 modules) translated, validated and adapted for the Bulgarian context and validated from Bulgarian experts | December 2025 (min 2 modules each month) |
| 5. Design and develop capacity building modules for ECI professionals,  | 2 university postgraduate programmes and one major course on ECI basics developed and implemented in 2 universities in the country  | October 2024 |
| 6. Conduct a National ECI Conference or policy event | Concept note, List of participants, Conference program, Report with recommendations  | October 2024 |
| 7. Technical support for the preparation of external evaluation of H&M project  | the package with materials and database are finalized and provided to the evaluators  | December 2025 |
| 8. Methodological support for introduction of Tier 3 of H&M project | Methodological package for provision of support for families with children with autism and cerebral policy is ready for testing in Nova Zagora and Haskovo municipalities | June 2024 |
| 9. Methodological support for adaptation of Tier 3 of H&M project | Methodological package for provision of support for families with children with autism and cerebral policy is adapted to the country context  | June 2025 |
| 10. Review and provide input for key policy documents on ECD, including ECD National Action Plan and strategic document on ECD | The draft of the ECI National Roadmap is available ECD vision draft is available  | 2024-2025 |
| 11. Technical support for the national implementation of the signed Rowing work plan  | Draft of the National Strategy for the Child and the implementation plans drafted and attached to the strategy other Input provided with argumentation | December 2024 |