## 1. PDM
PDM (Project Design Matrix) |  |  |  |  | As of November 22, 2022
• Project Title : Improvement of Access and Quality of Primary Education in Kinshasa, DRC
• Site : Nsele commune (Nsele 1, Nsele 2), Kinshasa
• Budget : 7.2M USD (KOICA 6.5M USD + UNICEF 0.7M USD)
• Duration : 2021-2025
• Beneficiaries: 50,965 persons (49,542 Students, 975 teachers, 108 school directors, 16 inspectors, 324 COPA members) in Nsele1 and 2 education subdivisions in Kinshasa
Narrative Summary | Verifiable Indicator | Means of Verification |  | Important Assumption
<Overall Goal>
1. By 2030, ensure that all girls and boys complete free, equitable and quality primary and secondary education leading to relevant and effective learning outcomes (SDG4.1) |  |  |  | There are no humanitarian emergencies in the targeted provinces and surrounding areas which leads to the mass movement of the population away into targeted areas.
2. By 2025, develop access and ensure equity (SSEF1)
<Project Purpose/Outcome>
1. Access to primary education for public school students is improved in a gender responsive way in Nsele 1 and Nsele 2 education subdivisions in Kinshasa Province | 1.a. Rate and Number of students who completed primary school (at least 50% girls) | - Partners’ reports (EPST report, TENAFEP results) |  | Classrooms are built as planned
| 1.b. Number of students benefiting from an improved school environment (at least 50% girls) | - Partners’ reports (EPST report, School records)
| 1.c. Students’ attendance rate (%) in public primary school | - Partners’ reports (EPST report, School records)
| 1.d. School survival rate | - Partners’ reports (EPST report, School records)
2.Quality of primary education for public school students is improved in Nsele 1 and Nsele 2 education subdivisions in Kinshasa Province | 2.a. Percentage (%) and Number of students who passed in French and Math | - Partners’ reports (EPST report, School records) |  | No interruptions to final year exams
| 2.b. Percentage (%) and Number of teachers who teach with improved knowledge and skills (at least 50% females) | - Self-efficacy survey
<Outputs>
1.1. Improved school facilities | 1.1.a. Number of schools benefiting improved school facilities | - Construction report |  | - All activities of partners fully following the planned schedules, especially construction activities - There are no significant changes in concepts and activities of the project - There is no severe inflation in the country - There are no teacher strikes during the project implementation - Teachers and inspectors put into practice what they learned in training
| 1.1.b. Number of classrooms constructed | - Construction report
| 1.1.c. Number of latrines constructed | - Construction report
1.2. Improved learning and teaching materials | 1.2.a. Number of distributed learning/teaching materials | - Partners’ reports (EPST)
| 1.2.b. Number of students who obtained improved access to learning materials | - Partners’ reports (EPST)
| 1.2.c. Number of students who benefited from reading sessions | - Partners’ reports (EPST, attendance list)
2.1. Enhanced literacy and numeracy achievement and children’s rights | 2.1.a. Number of students who participated in remedial classes | - Partners’ reports (EPST, attendance list)
| 2.1.b. Number of students who participated in each competition | - Partners’ reports (EPST/NGO, participant list)
| 2.1.c. Number of participants in the campaign promoting children's rights | - Partners’ reports (EPST, participant list)
| 2.1.d. Number of girls who received sexual and reproductive health education and MHM kits | - Partners’ reports (EPST/NGO)
| 2.1.e. Number of children’s rights committee members trained |  | - Partners’ reports (EPST/NGO)
| 2.1.f. Number of COPA members trained |  | - Partners’ reports (EPST, attendance list)
2.2. Strengthened education management skills and teaching methodology | 2.2.a. Number of inspectors trained |  | - Partners’ reports (EPST, attendance list)
| 2.2.b. Number of teachers trained |  | - Partners’ reports (EPST, attendance list)
| 2.2.c. Number of educational personnel trained | - Partners’ reports (EPST/NGO, attendance list)
<Activities> | <Inputs> |  |  | - Materials are available locally - Procurement is not delayed - Communities are actively involved in the project - There are enough participants who are willing to participate in the training as well as the activities - There are no significant changes in the Government’s basic education strategy - Parent committees are functional in all targeted schools - training modules and facilitators are available - Various stakeholders collaborate effectively
1.1.1. Construct Children’ classrooms and director’s office | KOICA |  | EPST
1.1.2. Construct multifunctional rooms in model schools | 6.5 M USD |  | 1. Securing Site and related permits for the school construction
1.1.3. Construct latrines and waterpoint |  |  | 2. Selection of counter personnel to manage and support the project
1.1.4. Furnish classrooms and director’s office/ model schools | UNICEF
0.7 M USD
1.2.1. Provide learning materials in multifunctional rooms
1.2.2. Provide textbooks and learning materials
1.2.3. Provide reading resources and organize reading sessions
1.2.4. Provide essential teaching materials and recreation kits (art, music, PE materials)
2.1.1. Conduct tailored remedial classes
2.1.2. Promote school competitions for literacy, numeracy, and children’s rights
2.1.3. Strengthen the capacities of the Children's rights committee
2.1.4. Strengthen the capacities of Parents committees
2.2.1. Conduct training for inspectors (ToT)
2.2.2. Conduct training for primary school teachers
2.2.3. Conduct educational statistics training

## 2. Result Tracking Sheet
Result Tracking Sheet
Title | Improvement of Access and Quality of Primary Education in Kinshasa, DRC
Prepared by | Mijeong Kim |  | Date | 2022-11-22
|  | Indicators |  | Items | Baseline (1st year) | 2nd Year | 3rd Year | 4th Year | Target
[5 empty] | 2022 | 2023 | 2024 | 2025 | 2025
outcome | 1. Access to primary education for public school students is improved in a gender responsive way in Nsele 1 and Nsele 2 education subdivisions in Kinshasa Province | 1.a. Rate and Number of students who completed primary school (at least 50% girls) |  | Data/Result | TBD |  |  |  | TBD
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST)
Achievement Rate
Achievement Rate / Overall
Outcome_Basis of Calculation
|  |  |  | Numerator | Number of last grade students who passed the TENAFEP in the target schools x 100 (%)
|  |  |  | Denominator | Total number of last grade students in the target schools
|  | 1.b. Number of students benefiting from an improved school environment (at least 50% girls) |  | Data/Result | 0 |  |  |  | 8472
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | 0 | 0 | 8,472
Achievement Rate
Achievement Rate / Overall
|  | 1.c. Students’ attendance rate (%) in public primary school |  | Data/Result | TBD |  |  |  | TBD
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST)
Achievement Rate
Achievement Rate / Overall
Outcome_Basis of Calculation
|  |  |  | Numerator | the sum of each student's attendance rate
|  |  |  | Denominator | the total number of students enrolled in the target schools
|  | 1.d. School survival rate |  | Data/Result | TBD |  |  |  | TBD
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST)
Achievement Rate
Achievement Rate / Overall
Outcome_Basis of Calculation
|  |  |  | Numerator | Number of students who reached 5th grade in the cohort x 100 (%)
|  |  |  | Denominator | Number of students who were enrolled in the 1st grade (cohort) in the target schools
| 2.Quality of primary education for public school students is improved in Nsele 1 and Nsele 2 education subdivisions in Kinshasa Province | 2.a. Percentage (%) and Number of students who passed in French and Math |  | Data/Result | French/ Maths 42% / 85% (Nsele 1) 46% / 78% (Nsele 2) (source: EPST Plateau report) |  |  |  | TBD
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST)
Achievement Rate
Achievement Rate / Overall
Outcome_Basis of Calculation
|  |  |  | Numerator | Number of students (grade 5,6) who passed at the end of the school year x 100 (%)
|  |  |  | Denominator | total number of students at grade 5,6 in the target schools
|  | 2.b. Percentage (%) and Number of teachers who teach with improved knowledge and skills (at least 50% females) |  | Data/Result | 0% |  |  |  | 85%
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 0 | 85%
Achievement Rate
Achievement Rate / Overall
Outcome_Basis of Calculation
|  |  |  | Numerator | Teachers who confirmed an improvement x 100 (%)
|  |  |  | Denominator | The number of teachers trained through this project
|  | Indicators |  | Items | Baseline | 1st Year | 2nd Year | 3rd Year | Target
[5 empty] | 2022 | 2023 | 2024 | 2025 | 2025
outputs | 1.1 Improved school facilities | 1.1.a. Number of schools benefiting improved school facilities |  | Data/Result | 0 |  |  |  | 10
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 10
Achievement Rate
Achievement Rate / Overall
|  | 1.1.b. Number of classrooms constructed |  | Data/Result | 0 |  |  |  | 60
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 60
Achievement Rate
Achievement Rate / Overall
|  | 1.1.c. Number of latrines constructed |  | Data/Result | 0 |  |  |  | 80
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 80
Achievement Rate
Achievement Rate / Overall
| 1.2. Improved learning and teaching materials | 1.2.a. Number of distributed learning/teaching materials |  | Data/Result | 0 |  |  |  | 134,386
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | 67,247 | 67,139
Achievement Rate
Achievement Rate / Overall
|  | 1.2.b. Number of students who obtained improved access to learning materials |  | Data/Result | 0 |  |  |  | 99084
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | 49542 | 49542
Achievement Rate
Achievement Rate / Overall
|  | 1.2.c. Number of students who benefited from reading sessions |  | Data/Result | 0 |  |  |  | TBD
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST) | TBD (to be determined after consultation with EPST)
Achievement Rate
Achievement Rate / Overall
| 2.1. Enhanced literacy and numeracy achievement and children’s rights | 2.1.a. Number of students who participated in remedial classes |  | Data/Result | 0 |  |  |  | 9908
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | 3963 | 3963 | 1982
Achievement Rate
Achievement Rate / Overall
|  | 2.1.b. Number of students who participated in each competition |  | Data/Result | 0 |  |  |  | 648
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 324 | 324
Achievement Rate
Achievement Rate / Overall
|  | 2.1.c. Number of participants in the campaign promoting children's rights |  | Data/Result | 0 |  |  |  | 648
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 324 | 324
Achievement Rate
Achievement Rate / Overall
|  | 2.1.d. Number of girls who received sexual and reproductive health education and MHM kits |  | Data/Result | 0 |  |  |  | 25408
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 12704 | 12704
Achievement Rate
Achievement Rate / Overall
|  | 2.1.e. Number of children’s rights committee members trained |  | Data/Result | 0 |  |  |  | 1296
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 1296
Achievement Rate
Achievement Rate / Overall
|  | 2.1.f. Number of COPA members trained |  | Data/Result | 0 |  |  |  | 324
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 324
Achievement Rate
Achievement Rate / Overall
| 2.2. Strengthened education management skills and teaching methodology | 2.2.a. Number of inspectors trained |  | Data/Result | 0 |  |  |  | 16
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 16
Achievement Rate
Achievement Rate / Overall
|  | 2.2.b. Number of teachers trained |  | Data/Result | 0 |  |  |  | 975
|  |  |  | Annual Result | Annual Result
[5 empty] | Target |  | 975
Achievement Rate
Achievement Rate / Overall
|  | 2.2.c. Number of educational personnel trained |  | Data/Result | 0 |  |  |  | 232
|  |  |  | Annual Result | Annual Result
[5 empty] | Target | 232
Achievement Rate
Achievement Rate / Overall

## 3. List of Key Indicators
Key Indicators (Outcomes, Outputs) Definition
[Outcome]
indicator | Rate and Number of students who completed primary school (at least 50% girls) | indicator code | 1.a
definition | Rate and Number of students who completed the primary education by passing TENAFEP (National Test of the End of Primary Studies)
unit of measurement/measurement method | Number of last grade students who passed the TENAFEP in the target schools x 100 (%)
Total number of last grade students in the target schools
data collection and source | Source: EPST report, TENAFEP results
proxy indicator | SDG 4.1.2 Completion rate (primary education), by sex
others | Sex-disaggregated data
School-disaggregated data
indicator | Number of students benefiting from an improved school environment (at least 50% girls) | indicator code | 1.b
definition | Number of students enrolled in schools whose facilities and materials have been improved through this project (at least 50% girls)
unit of measurement/measurement method | Numerical quantity
data collection and source | Source: EPST report, school records
proxy indicator
others | Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
indicator | Students’ attendance rate in public primary school | indicator code | 1.c
definition | the average attendance rate* of students in the target schools *attendance rate:
the number of days a student attended at school x 100% the total number of days a student is required to be attended
unit of measurement/measurement method | the sum of each student's attendance rate
the total number of students enrolled in the target schools
data collection and source | Source: EPST report, school records
proxy indicator
others | Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
indicator | School survival rate | indicator code | 1.d
definition | Proportion of a cohort of students enrolled in the first grade of the target primary schools who have reached the 5th grade
unit of measurement/measurement method | Number of students who reached 5th grade in the cohort x 100 (%)
Number of students who were enrolled in the 1st grade (cohort) in the target schools
data collection and source | Source: school records, EPST report
proxy indicator
others | Sex-disaggregated data
School-disaggregated data
indicator | Percentage (%) and Number of students who passed in French and Math | indicator code | 2.a
definition | students at 5th and 6th grades in the target schools who passed the national standard required at the end of the school year for French and Maths
unit of measurement/measurement method | Number of students (grade 5,6) who passed at the end of the school year x 100 (%)
total number of students at grade 5,6 in the target schools
data collection and source | Data collection: EPST reports, school records
proxy indicator
others | Subject-disaggregated data
Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
indicator | Percentage (%) and Number of teachers who teach with improved knowledge and skills (at least 50% females) | indicator code | 2.b
definition | - Percentage and number of teachers who confirmed an improvement in their knowledge and teaching skills through this project
unit of measurement/measurement method | Teachers who confirmed an improvement x 100 (%)
Number of teachers trained through this project
data collection and source | Data collection: self-efficacy survey for teachers at target schools
proxy indicator
others | Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
[Output]
indicator | Number of schools benefiting improved school facilities | indicator code | 1.1.a.
definition | Number of schools whose facilities have been improved through this project
unit of measurement/measurement method | Numerical quantity
data collection and source | construction report
proxy indicator
others
indicator | Number of classrooms constructed | indicator code | 1.1.b
definition | Number of classrooms built through this project
unit of measurement/measurement method | Numerical quantity
data collection and source | construction report
proxy indicator
others
indicator | Number of latrines constructed | indicator code | 1.1.c
definition | Number of latrines built through this project one door is one latrine
unit of measurement/measurement method | Numerical quantity
data collection and source | construction report
proxy indicator
others
indicator | Number of distributed learning and teaching materials | indicator code | 1.2.a
definition | Learning materials are two kinds- 1) an individual school kit is a bag with various tools such as pencils, notebooks, etc. 2) a package of Textbooks per student at grade 5 and 6 Teaching materials are two kinds - 1) individual teacher's kit is a package of various essential teaching tools such as pens, chalks, etc. 2) recreation kit is a package of Art, Music, PE materials. This indicator counts the number of 'kit' and textbooks distributed from UNICEF and/or MEPST to public primary schools
unit of measurement/measurement method | Numerical quantity - Number of Kits (individual school kit, individual teacher's kit, recreation kit) - Number of textbooks distributed from UNICEF and/or MEPST to target schools through this project
data collection and source | Data collection: Progress report (Survey)
Source: EPST report (distribution list)
proxy indicator
others | Sex-aggregated data
indicator | Number of students who obtained improved access to learning materials | indicator code | 1.2.b
definition | Children who obtained improved access to learning materials means students who received the kits (individual school kit) and/or at least one subject of textbooks
unit of measurement/measurement method | Numerical quantity - Number of students in target schools who received an individual school kit and/or at least one subject of textbooks
data collection and source | Data collection: Progress report (Survey)
Source: EPST report
proxy indicator
others | Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
indicator | Number of students who benefited from reading sessions | indicator code | 1.2.c
definition | Number of students who attended the reading sessions at least once
unit of measurement/measurement method | Numerical quantity
data collection and source | Data collection: attendance list
Source: EPST report
proxy indicator
others | Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
indicator | Number of students who participated in remedial classes | indicator code | 2.1.a
definition | Number of students who attended the remedial classes at least four times
unit of measurement/measurement method | Numerical quantity
data collection and source | Data collection: attendance list
Source: EPST report
proxy indicator
others | Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
indicator | Number of students who participated in each competition | indicator code | 2.1.b
definition | Number of students who have been selected for the competition at the model schools
unit of measurement/measurement method | Numerical quantity
data collection and source | Data collection: participants list
Source: EPST/NGO report
proxy indicator
others | Subject-disaggregated data
Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
indicator | Number of participants in the campaign promoting children's rights | indicator code | 2.1.c
definition | Number of persons who read the posters promoting children's rights or/and received messages of the posters - Director and teachers will explain the children's rights to students, using the posters.
unit of measurement/measurement method | Numerical quantity
data collection and source | Data collection: Participant list
Source: EPST report
proxy indicator
others | Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
indicator | Number of girls who received sexual and reproductive health education and MHM kits | indicator code | 2.1.d
definition | Number of girls who received sexual and reproductive health education and MHM kits at least once during the project period, regardless of their age and grade in the target schools
unit of measurement/measurement method | Numerical quantity
data collection and source | Source: EPST/NGO report
proxy indicator
others | Sex-disaggregated data
Grade-disaggregated data
School-disaggregated data
indicator | Number of children’s rights committee members trained | indicator code | 2.1.e
definition | the number of children's committee members that have benefited from capacity building activities in hygiene, MHM as well as children's rights to education (at least 3/5 activities)
unit of measurement/measurement method | Numerical quantity
data collection and source | Source: EPST/NGO report
proxy indicator
others | At least 30% of the training participants in total are girls
Sex-disaggregated data
School-disaggregated data
indicator | Number of COPA members trained | indicator code | 2.1.f
definition | the number of parents' committee (COPA) members that have benefited from capacity building activities in planning, monitoring and management as well as children's rights at least 3/5 of the training courses
unit of measurement/measurement method | Numerical quantity
data collection and source | Data collection: Attendance list
Source: EPST report
proxy indicator
others | At least 30% of the training participants in total are female
Sex-disaggregated data
School-disaggregated data
indicator | Number of inspectors trained | indicator code | 2.2.a
definition | the number of inspectors who have completed at least 3/5 of the training course
unit of measurement/measurement method | Numerical quantity
data collection and source | Data collection: Attendance list
Source: EPST report
proxy indicator
others | Sex-disaggregated data
indicator | Number of teachers trained | indicator code | 2.2.b
definition | the number of teachers who have completed at least 3/5 of the training course on national curricula and classroom management
unit of measurement/measurement method | Numerical quantity
data collection and source | Data collection: Attendance list
Source: EPST report
proxy indicator
others | Sex-disaggregated data
School-disaggregated data
indicator | Number of educational personnel trained | indicator code | 2.2.c
definition | the number of educational personnel who have completed at least 3/5 of the training course - educational personnel includes school director, inspector and teachers
unit of measurement/measurement method | Numerical quantity
data collection and source | Data collection: Attendance list
Source: EPST/NGO report
proxy indicator
others | Sex-disaggregated data
School-disaggregated data

## 4. Detailed Indicators Template
Detailed Performance Indicators (disaggregated)
|  |  | 1.a. Rate and Number of students who completed primary school (at least 50% girls) |  |  |  | 1.b. Number of students benefiting from an improved school environment (at least 50% girls) |  |  |  | 1.c. Students’ attendance rate (%) in public primary school |  |  |  | 1.d. School survival rate |  |  |  | 2.a.1. Percentage (%) and Number of students who passed in French |  |  |  | 2.a.2. Percentage (%) and Number of students who passed in and Math |  |  |  | 2.b. Percentage (%) and Number of teachers who teach with improved knowledge and skills (at least 50% females) |  |  |  | 1.1.a. Number of schools benefiting improved school facilities |  |  |  | 1.1.b. Number of classrooms constructed |  |  |  | 1.1.c. Number of latrines constructed |  |  |  | 1.2.a. Number of distributed learning/teaching materials |  |  |  | 1.2.a. Number of distributed learning/teaching materials |  |  |  | 1.2.b. Number of students who obtained improved access to learning materials |  |  |  | 1.2.c. Number of students who benefited from reading sessions |  |  |  | 2.1.a. Number of students who participated in remedial classes |  |  |  | 2.1.b.1. Number of students who participated in each competition (French) |  |  |  | 2.1.b.2. Number of students who participated in each competition (Math) |  |  |  | 2.1.b.3. Number of students who participated in each competition (Children's rights) |  |  |  | 2.1.c. Number of participants in the campaign promoting children's rights |  |  |  | 2.1.d. Number of girls who received sexual and reproductive health education and MHM kits |  |  |  | 2.1.e. Number of children’s committee members trained |  |  |  | 2.1.f. Number of COPA members trained |  |  |  | 2.2.a. Number of inspectors trained |  |  |  | 2.2.b. Number of teachers trained |  |  |  | 2.2.c. Number of educational personnel trained
|  |  | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate
N. Subdivision / School name | 2022 | Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Total
| 2023 | Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Total
| 2024 | Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Total
| 2025 | Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Total
|  |  | 1.a. Rate and Number of students who completed primary school (at least 50% girls) |  |  |  | 1.b. Number of students benefiting from an improved school environment (at least 50% girls) |  |  |  | 1.c. Students’ attendance rate (%) in public primary school |  |  |  | 1.d. School survival rate |  |  |  | 2.a.1. Percentage (%) and Number of students who passed in French |  |  |  | 2.a.2. Percentage (%) and Number of students who passed in and Math |  |  |  | 2.b. Percentage (%) and Number of teachers who teach with improved knowledge and skills (at least 50% females) |  |  |  | 1.1.a. Number of schools benefiting improved school facilities |  |  |  | 1.1.b. Number of classrooms constructed |  |  |  | 1.1.c. Number of latrines constructed |  |  |  | 1.2.a. Number of distributed learning/teaching materials |  |  |  | 1.2.a. Number of distributed learning/teaching materials |  |  |  | 1.2.b. Number of students who obtained improved access to learning materials |  |  |  | 1.2.c. Number of students who benefited from reading sessions |  |  |  | 2.1.a. Number of students who participated in remedial classes |  |  |  | 2.1.b.1. Number of students who participated in each competition (French) |  |  |  | 2.1.b.2. Number of students who participated in each competition (Math) |  |  |  | 2.1.b.3. Number of students who participated in each competition (Children's rights) |  |  |  | 2.1.b.3. Number of students who participated in each competition (Children's rights) |  |  |  | 2.1.c. Number of girls who received sexual and reproductive health education and MHM kits |  |  |  | 2.1.d. Number of children’s committee members trained |  |  |  | 2.1.e. Number of COPA members trained |  |  |  | 2.2.a. Number of inspectors trained |  |  |  | 2.2.b. Number of teachers trained |  |  |  | 2.2.c. Number of educational personnel trained
|  |  | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate | Female | Male | Total | Rate
N. (Subdivision) n. School name | 2022 | Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Total
| 2023 | Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Total
| 2024 | Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Total
| 2025 | Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Total