## Sheet1
Financial Proposal Individual consultancy to conduct data analysis of the existing Educational Management Information Systems (EMIS) and provide further improvement recommendations to ensure relevant and accurate data is available
Applicant name
Address
Contact info
Date
Offer validity (days)
Consultancy
Tasks | Deliverable | Timeline* | Fee to complete deliverable (MDL)
Conduct desk review of documentation on EMIS and analyze the available data in EMIS, data collection process, including national and international best practices and data from relevant institutions. | The desk review report containing main findings and recommendations for report development | 3 working days | 0
- Conduct relevant interviews and focus group discussions with MER departments, UNICEF, National Agency for Quality Assurance in Education (NAQAE), National Curriculum and Evaluation Agency (NACE), Centre of ICT in Education (CICTE), e-Governance Agency Moldova, local departments of education, educational institutions, and other relevant actors | -List of interviewed people | 5 working days | 0
- Apply analytical methodology and tools to interviews and data | - A summary report on the key findings including new data and recommendations
Develop the draft of EMIS data analysis report and provide recommendations to ensure that relevant and accurate data is available to comply with the needs of Ministry of Education and Research, educational institutions and other relevant institutions. | First draft of the EMIS data analysis and recommendations report developed | 10 working days | 0
Based on received feedback, finalized the EMIS report with recommendations | Final draft of the EMIS data analysis and recommendations report developed | 2 working days | 0
Total: |  | 20 working days
Other costs ( if relevant)
Type of expenditures ( e.g translation ) (and corresponding activity) |  |  | Unit | Cost (MDL) per Unit | Sub-total
Other (if applicable, please add more lines and specify details in brackets) Travel fees should be estimated |  |  | 1 |  | 0
Sub-total Other costs |  |  | X | X
Total Financial Proposal (MDL) |  |  |  |  | 0