**Financial proposal**

**Assignment**: **National Consultant-Evidence Generation on Teacher Training and Preparedness UNICEF Ghana, Accra**

**Proposal from:**

**Proposal To**:

**Kindly provide your proposed all-inclusive fee (Professional fee, subsistence allowance, transport cost etc.) as per the deliverables listed below. Kindly note fee should be quoted in the local currency (Ghana Cedis).**

**Proposed daily professional fee: GHS**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deliverables**  | **Estimated no. of days**  | **Deadline**  | **Budget (GHS)**  |
| 1. Evidence generation plan for tracking teacher preparedness co-developed alongside government and UNICEF counterparts. Including key data collection instruments and protocols for monitoring teacher training effectiveness and delivery of DL classes co-designed/adapted in conjunction with governmental counterparts  | 10 | 30-Nov-24  |  |
| 2. Clean quantitative dataset on training monitoring produced, and analysis performed incorporating guidance from UNICEF and government counterparts | 15  | 15-Dec-24  |   |
| 3. **First round** of qualitative primary data collection (in-depth interviews and conducting focus group discussions with school stakeholders) undertaken in 12-15 schools across the 03 districts, including providing transcriptions of qualitative research in English.  | 15 | 15-Jan-24 |  |
| 4. Mid-term brief on preliminary evidence produced, incorporating input from government and UNICEF counterparts, and Mid-term feedback session with all relevant counterparts organized  | 5 | 3-Feb-25  |   |
| 5. Support and capacity building provided at the school level in the execution of government’s ongoing monitoring activities, in liaison with government and UNICEF. | 10  | 28-Feb-25  |   |
| 6. **Second round** of qualitative primary data collection (in-depth interviews and conducting focus group discussions with school stakeholders) undertaken in 12-15 schools across the 03 districts, including providing transcriptions of qualitative research in English.  | 15 | 30-Mar-25 |  |
| 7. Verification and cleaning of secondary data collected from schools  | 15 | 30-Mar-25  |   |
| 8. Research report produced on evidence findings and lessons learnt on DL teacher preparedness, incorporating feedback from UNICEF and government counterparts  | 10  | 15-Apr-25  |   |
| 9. Final Report shared (Workshop organized to disseminate and validate results with government and UNICEF counterparts, and schools + additional dissemination activities performed, including participation in online and in-person events/conferences and) development of policy notes).  | 5  | 15-Apr-25  |   |
| **Total Number of Days:** | 100  |  |  |
| **Total Cost in Ghana Cedis:** |  |  |  |

|  |
| --- |
| **Other expenses related to travel (Kindly include all travel related cost)** |
|  | **Cost Estimate** | **Qty** |
| Local Travel  | Six (6) trips (local travel) to the field locations: * Ayensuano (2 trips in total; each trip 5 days)
* Asunafo North (2 trips in total; each trip 5 days)
* Assin South (2 trips in total; each trip 5 days)
 |  | 3030 |
| DSA | Expected to travel to field and spend 30 days for field related work which forms part of the deliverables. |  |  |