| **DELIVERABLES** | **DURATION CVA Consultant** | **DURATION MBP consultant** |
| --- | --- | --- |
| **Database of knowledge resources on CVA and MBP for WASH, evidence maps, and report outlining gap areas and quality issues** |
| Preparatory work ahead of mission to Geneva | 2 days | 2 days |
| Inception mission to Geneva | 3 days  | 3 days |
| Development of work plan and methodology | 1 day | 1 day |
| Development of a list of criteria to evaluate the quality of existing knowledge | 2 days  | 2 days |
| Remote data collection with national WASH clusters, and GWC global partners | 10 days  | 10 days |
| Review of collected data and of data already in the GWC repository for classification purposes, and to identify gap areas and quality issues | 10 days  | 10 days |
| First draft of evidence maps and of report on gaps and quality | 5 days  | 5 days |
| Consolidation of inputs from the two consultants for evidence maps and report on gaps and quality | 3 days |
| Review process of first draft, including consultations with the GWC Cash and Markets TWIG | 3 days  | 3 days |
| Final draft of evidence maps and of report on gaps and quality | 2 days  | 2 days |
| **Report on MPC and WASH** |
| Review of collected data and of data already in the GWC repository to identify practices related to MPC and WASH, impact of MPC on WASH outcomes, and WASH programming complementary to MPC | 8 days | n/a |
| Key informant interviews[[1]](#footnote-1) | 4 days | 1 day |
| First draft of report on MPC and WASH | 10 days | 2 days |
| Review process of first draft, including consultations with the GWC Cash and Markets TWIG | 5 days | n/a |
| Final draft of report on MPC and WASH | 5 days | 1 day |
| **Three reports on CVA and MPB for WASH** |
| Review of collected data and of data already in the GWC repository to identify practices related to CVA and MBP, impact of CVA and MBP on WASH outcomes, and complementary WASH programming (for each of the 3 WASH areas) | 5 days X 3 | 5 days X 3 |
| Key informant interviews[[2]](#footnote-2) (for each of the 3 WASH areas) | 2 days X 3 | 3 days X 3 |
| First draft of report (for each of the 3 WASH areas) | 8 days X 3 | 8 days X 3 |
| Consolidation of first draft of report (for each of the 3 WASH areas) | 1.5 days X 3 |
| Presentation / validation of the report (second mission to GVA) | 2 days  | 2 days |
| Review process of first draft (for each of the 3 WASH areas) | 3 days X 3 | 3 days X 3 |
| Final draft of report (for each of the 3 WASH areas) | 3 days X 3 | 3 days X 3 |
| Review of any issues related to the consolidation of the report in the final draft (for each of the 3 WASH areas) | 0.5 days X 3 |

1. To be discussed and adjusted during inception mission [↑](#footnote-ref-1)
2. To be discussed and adjusted during inception mission [↑](#footnote-ref-2)