**Kindly provide your proposed all-inclusive fee (Professional fee, subsistence allowance, transport cost etc.) as per the deliverables listed below.**

|  |  |  |  |
| --- | --- | --- | --- |
| Work Assignments Overview | Deliverables/Outputs | Delivery deadline | Estimated Budget (GHS) |
| Reviewing and development of a comprehensive strategic documents to guide the roll-out of the LP/GME in an equitable and research-informed manner and measure learning outcomes. | 1. Inception report detailing project delivery details including timelines, tasks, modalities of execution, etc. developed.
 | 30th October 2023 |   |
| 1. A comprehensive LP/GME implementation plan with a costed strategy/plan, developed and approved.
 | 3rd November 2023 |   |
| 1. LP/GME MEL framework incorporating the implementation research plans/tools to measure learning; and school EdTech Infrastructure delivery checklist, developed and approved.
 | 10th November 2023 |   |
| Improve national and sub-national systems and capacities to deliver LP/GME in a coordinated approach | 1. Agencies, initiatives, and interventions on EdTech in schools and communities, mapped, including stakeholder mapping and analyses within connectivity and devices ecosystem; and leveraging and entry points established and utilised.
 | 20th November 2023 |  |
| 1. At least 12 (once per month) strategic engagements with key agencies for leveraging support held and key action points delivered.
 | 30th September 2024 |  |
| 1. Educational functionaries, teachers, PTAs, SMCs, students, etc. in project districts trained and oriented to support the delivery of LP/GME.
 | 30th June 2024 |  |
| 1. LP/GME ease of use User guides for teachers, students, education functionaries, and parents developed.
 | 20th September 2024 |   |
| Enhance students sustained engagement and interest on LP/GME usage for improving learning outcomes | 1. LP/GME students and youth champions to support advocacy and uptake of the solutions by learners, created in at least 18 project schools.
 | 30th June 2024 |   |
| 1. LP/GME intra/inter-schools innovative engagement modalities established, initiated, and documented.
 | 30th June 2024 |   |
| 1. Variety of inclusive and multimedia contents for Literacy, Numeracy, mapped, curriculum aligned and uploaded on the LP platform.
 | 30th September 2024 |   |
| Increase coordination, research, learning, advocacy, and accountability for the enhanced roll-out of the GME | 1. Two (2) LP/GME implementation review meetings with project districts for informed decisions, conducted.
 | 30th September 2024 |  |
| 1. At least, two (2) school level monitoring exercises per each of the project schools, completed.
 | 30th August 2024 |   |
| 1. At least, a school term of LP/GME implementation research in project schools, completed
 | 30th January 2024 |  |
| Increase LP/GME solutions deployments sustainability and funding to support scale-up. | 1. LP/GME evidence-informed investment case and sustainability plan, developed
 | 30th August 2024 |   |
| 1. LP/GME roll-out captured in project districts ADEOPs.
 | 30th September 2024 |   |
| 1. At least three (3) human Interest stories on project delivery, developed
 | 30th September 2024 |  |
| Project Reporting | 1. Mid-year project progress report submitted
 | 20th March 2024 |  |
| 1. End of project report submitted
 | 15th October 2024 |  |
| **Total** |  |  |  |