## Sheet1
Financial Proposal for National Individual Consultant: Public Financial Management (PFM) Specialist to enable the piloting of Pre-school Education Services funding schemes in the Republic of Moldova
Applicant name
Address
Contact info
Date
Offer validity (days)
Consultancy
Deliverable | Number of working days | Consultancy fee (daily rate, MDL) | Sub- total
Inception Report, including: -Plan of activities - Desk review of available and related analyses - Assessment of available data - Methodology and roadmap | 15 |  | 0
Deliverable 2 Budget database compiled and presented to UNICEF, the MECR and the Education Economist | 30 |  | 0
Deliverable 3 Comparative analysis report produced (max 10 pages) | 20 |  | 0
Deliverable 4 - Draft Report and Roadmap available - At least 2 meetings organized with MECR, and local authorities to validate the recommendations | 15 |  | 0
Deliverable 5 At least 5 consultations meetings organized with local authorities and stakeholders | 15 |  | 0
Deliverable 6 Trainings on PFM organized | 45 |  | 0
Deliverable 6 Final Report and Road Map submitted | 10 |  | 0
Sub-total Consultancy fee | 150 |  | 0
Other costs ( if relevant)
Type of expenditures | Unit ( daily, hours , page etc.) | Unit cost, MDL per day, hour, page etc. | Sub-total
logistics linked to meetings organization |  |  | 0
local transportation costs |  |  | 0
Other (if applicable, please add more lines and specify details in brackets ) |  |  | 0
Sub-total Other costs | X | X | 0
Total, MDL, financial proposal |  |  | 0