## Sheet1
Financial Proposal National Individual consultancy to support ECD team in development of the formal and non-formal educational video materials and community mobilization activities under the Lego Foundation funded project
Applicant name
Address
Contact info
Date
Offer validity (days)
Consultancy
Deliverable | No of days | Daily Fee (MDL) | Sub- total
1.1. Inception report and work plan agreed with the supervisor | 1 |  | 0
2.1. Informational materials on ECI distributed in 35 districts; 2.2 Develop concept-note on the topics to be discussed and questions at the TV shows; 2.3 Participation of the ECI experts in TV shows organized and supported | 4 |  | 0
3.1. Develop the concept note of the event and consulted and approved by the supervisor 3.2. Coordination and approval of the informational/educational materials with MER, RO and LEGO Foundation 3.3. Technical report of the conference presented and approved by the supervisor | 12 |  | 0
4.1. Concept note and training plan approved by the supervisor 4.2. ToR for logistic services announced 4.3. Development of the concept note for educational video materials submitted and approved by the supervisor 4.4. Educational video materials developed and approved by the supervisor and SBC team and distributed on relevant channels 4.5 The final report on the training courses submitted and approved | 12 |  | 0
5.1. The concept note of the community group of trainers and its strategy to increase the number of ECE members presented and approved 5.2. Coordinate the team of master trainers and content of the community group; 5.3. The community group on social media functional and populated with content | 27 |  | 0
6.1. Define and coordinate translation of regional digital content of ECD materials 6.2. Define and coordinate translation of regional digital content of ECE materials 6.3. Digitalize local content of ECD materials (including ECI, GMCD, etc.) 6.4. Digitalize local content of ECE materials (including Lego) 6.5. Digital platform on ECD with regional and local content available and functional 6.6. Digital platform on ECE with regional and local content available and functional | 80 |  | 0
7.1. Desk review and Strategy/Activity Plan developed and approved by the supervisor 7.2. Action plan and recommendations presented to respective audience 7.3. Training modules developed and coordinated for further implementation 7.4. Lessons learnt presented based of parents’ feedback | 14 |  | 0
8.1. Coordinate the finalization of the ongoing contract on Bebbo promotion; 8.2 Present lessons learnt, and possible promotional scenarios based on focus-group results. New contract with the communication contractor signed 8.3. Bebbo CMS adjusted 8.4. Participation in all Bebbo coordination meetings with the RO 8.5. Bebbo app mainstreamed through different events such as breastfeeding week, immunization week, parenting month and mental health day. | 15 |  | 0
9.1. Concept note presented and approved by the supervisor; 9.2. Educational materials on EDU Tech Labs developed, approved and placed on social media/UNICEF webpage; 9.3. All relevant educational materials (booklets, leaflets etc.) distributed; 9.4. Educational video materials assistive technologies developed, approved, and distributed on relevant channels 9.5. Educational video materials on EDU Tech Labs distributed on relevant channels | 12 |  | 0
10.1 Final technical report presented and agreed by the supervisor | 1 |  | 0
Sub-total Consultancy fee | 0
Other costs ( if relevant)
Type of expenditures ( e.g translation ) (and corresponding activity) | Unit | Unit cost (MDL) | Sub-total
Other (if applicable, please add more lines and specify details in brackets) |  |  | 0
Sub-total Other costs | X | X | 0
Total Financial Proposal (MDL) |  |  | 0