|  |
| --- |
| Short-term individual consultant/ expert on guided play activities EDU/TURA/2021-MM |
| **Links with Country Programme Priorities****Ministry of National Education—UNICEF Education Programme 2021-2022 Rolling Work Plan****UNICEF Turkey Country Programme Document 2021-2025****Outcome 1. Early Childhood Development: By 2025, more young children, especially the most vulnerable, benefit from learning, nurturing, care and development at home and in their communities.****Output 1.2. Quality and inclusive ECE services: By 2025, the education system has increased capacity to provide quality and inclusive ECE services.** **Activity: 002 – Strengthen Quality and Access to Formal ECE Services Programme**Grant Code: SC200626 |

|  |
| --- |
|  **PROPOSED PAYMENT SCHEDULE** |
| **TASK**  | **DELIVERABLE** | **ESTIMATED PERSON/ DAY** | **TOTAL COST (TRY)** |
| 1 | Provide regular online/face to face technical support for teachers to conduct guided play sessions. | Technical support is provided regularly (through regular teacher-consultant interaction) | 14 days per consultant (two days per month) |  |
| 2 | Conduct regular field monitoring visits to schools where teachers implement the guided play (learning through play) activities in 20 pilot provinces. | One pager monitoring report after the completion each field visit. | 35 days per consultant (5 days per month) |  |
| 3 | Conduct trainings on guided play sessions for teachers from municipalities and ministries (online/face to face). | Trainings conducted if required (if not required no fee implication. | 18 days per consultant |  |
| 4 | Prepare and submit a final report outliningthe implementation processes in the field and making recommendations for the possible second phase. | Final report.  | 3 days per consultant |  |
| ***GRAND TOTAL (TRY):***  |  |

|  |
| --- |
| **NOTES** |
| **All fee rates must cover:** |
| *-  The remuneration actually paid to the experts concerned per person/ day* |
| *-  Administrative costs of employing the relevant experts, such as relocation and repatriation expenses* |
| *-  Expatriation allowances, leave, medical insurance, and other employment benefits**accorded to the experts by the Consultancy Company/Consultant* |
| *-  The margin, covering the consultant’s overheads, profit, and backstopping facilities* |
| *-  Note that the input of experts must be given in full working days* |
| **The number of person-days for each task shows the maximum number of days the consultant can work to deliver the related task. Suppose the consultant delivers the tasks by working fewer days than indicated in the financial submission. In that case, the task is considered completed, and the consultant may not need to work more on that task.** |