EXPRESSION OF INTEREST

National consultant for training and capacity building of WASH partners on WASH in Emergencies

Consultant Summary Profile: Please attach complete Curriculum Vitae

| Name |  |
| --- | --- |
| Date of Birth |  |
| Email address |  |
| Languages |  |
| Degrees/qualifications |  |
| Experience in carrying out similar (no. of years and key clients, including UN) |  |
| Attach one sample of similar work done or refer to a site that can be accessed. |  |
| List names and emails of three referees (Need to be former employment supervisors) |  |

Q1:  UNICEF’s humanitarian WASH response is delivered through a network of national and international Civil Society Organisations (CSO) and independent service providers. Post February 2021 military takeover, and in response to the rapidly unfolding crisis, the WASH response was expanded across the country through a network of implementing partners. The WASH partner staff come with varying skills, knowledge and understanding of the humanitarian WASH response.

It is proposed to tailor the WASH in Emergency training module and create a resource pool (master trainers) to strengthen the humanitarian WASH response capacity. Further the consultant is expected to train the WASH functionaries and community volunteers, as well as orient the senior managers.

Please review the detailed scope outlined in the Vacancy Announcement/ Terms of Reference in conjunction with the above and suggest a suitable approach and methodology (maximum 500 words) to successfully accomplish the assignment deliverables.

Q2: Given the duration of the assignment and deliverables please indicate your all-inclusive offer. The all-inclusive proposed fees should include all costs deemed necessary to undertake the assignment. Please link your fees directly to the specified deliverables.

The expected travel locations and frequencies are listed below in Annex I, so that the applicant can factor in these costs and propose all-inclusive amount.

Remark: Selected consultants must provide proof of medical insurance coverage valid for the period of the contract including coverage for medical evacuation.

| Deliverables | All inclusive Fee per Deliverable (In US$) |
| --- | --- |
| Inception report: detailed workplan, TNA plan, proposed training schedules. |  |
| Training needs assessment report |  |
| Training modules Five-day WiE training module Three-day WiE training module One day WiE orientation module The modules shall be submitted in a digital form, well-designed, proofread and ready to print. |  |
| Report on formation of the WiE resource group |  |
| Well trained resource pool and a report A well-trained resource pool comprising of at least seven members, Report on the training of resource pool (including the outcome, identifying the potential trainers. |  |
| Training and orientation for WASH partners At least ten 5-day training sessions conducted for WASH partners At least three 1-day orientation sessions conducted for senior management of the WASH partners | ……… $ per 5 day training session x 10 = ……. $ total …………… $ per 1 day orientation session x 3 = …….$ total |
| A final compilation and process documentation of the entire assignment process |  |
| Total (100%) |  |

Q3. The assignment is scheduled to begin in May 2023 for total of eleven months (Home-based with travel to the field for ~82 days of the contract period ). Please indicate your earliest availability and ability to work continuously.

Q4.  If not successful in participating in this round of consultancy, would you be interested to be considered for possible future similar consultancy?

Annex I: Travel locations and Frequencies

| No | Month | Frequency of travel | Duration of stay (days) | Region/ State | Townships expected to visit |
| --- | --- | --- | --- | --- | --- |
| 1 | May 2023 | 1 | 5 | Rakhine | Sittwe |
| 2 | June 2023 | 2 | 7 | Kachin, Kayin | Myitkyina, Hpa-An |
| 3 | July 2023 | 1 | 3 | Northern Shan | Lashio |
| 4 | August 2023 | 1 | 10 | Rakhine | Sittwe |
| 5 | September 2023 | 1 | 10 | Kachin | Myitkyina |
| 6 | October 2023 | 1 | 10 | Kayin | Hpa-An |
| 7 | November 2023 | 1 | 10 | Northern Shan | Lashio |
| 8 | December 2023 | 1 | 10 | Southern Shan | Taunggyi |
| 9 | January 2024 | 1 | 10 | Mandalay | Mandalay |
| 10 | February 2024 | 1 | 7 | Yangon | Yangon |

Annex II: Suggestive outline of the five-day training module

Day 1: 	Introduction to WASH in Emergencies and Child Rights Convention

- Introduction to the training program

- Icebreaker activity

- Overview of the WASH sector and its role in emergency response

- Principles of emergency response

- Impact of emergencies on WASH services

- Importance of effective coordination

- Introduction to the Child Rights Convention and its implications for WASH in emergencies

- Group discussion on challenges and opportunities in WASH emergency response

- Facilitator's guidebook: Introduction to WASH in Emergencies and Child Rights Convention

Day 2: 	Water Supply and Sphere Standards

- Recap of Day 1

- Water source selection

- Water treatment methods

- Distribution systems

- Water quality monitoring

- Practical exercise on water treatment and distribution

- Practical setting on installation of water storage tank and distribution system

- Introduction to Sphere standards and their relevance to water supply in emergencies

- Group discussion on key challenges in providing safe water in emergency situations

- Facilitator's guidebook: Water Supply in Emergencies and Sphere Standards

Day 3: Sanitation and Sphere Standards

- Recap of Day 2

- Sanitation facility design and construction

- Waste management

- Hygiene promotion

- Practical exercise on sanitation facility design and construction of emergency latrines including bathing spaces

- Practical demonstrations of safe pit emptying transport and disposal or onsite containment of excreta

- Introduction to Sphere standards and their relevance to sanitation in emergencies

- Group discussion on key challenges in providing safe sanitation in emergency situations

- Facilitator's guidebook: Sanitation in Emergencies and Sphere Standards

Day 4: Hygiene Promotion, WASH in Health Facilities, and Rapid Assessments

- Recap of Day 3

- Importance of hygiene promotion in preventing the spread of disease

- Handwashing promotion

- Practical session on installation of handwashing facilities including safe drainage

- Menstrual hygiene management

- Safe water storage and handling

- Design and construction of WASH facilities in health facilities

- Introduction to rapid assessments and their role in emergency response

- Group discussion on key challenges in promoting hygiene and providing WASH services in health facilities

- Practical exercise on rapid assessments

- Facilitator's guidebook: Hygiene Promotion, WASH in Health Facilities, and Rapid Assessments in Emergencies

Day 5: Monitoring and Evaluation

- Recap of Day 4

- Importance of monitoring and evaluation in WASH emergency response

- Development of monitoring and evaluation plans

- Data collection methods

- Data analysis

- Group discussion on best practices in monitoring and evaluating WASH interventions in emergency situations

- Feedback and evaluation of the training program

- Facilitator's guidebook: Monitoring and Evaluation in WASH Emergencies

The facilitator's guidebook could include detailed lesson plans for each day, along with suggested timings, learning objectives, and teaching methodologies. It could also include training materials such as PowerPoint presentations, handouts, and practical exercises. The guidebook could also provide tips and guidance on facilitating group discussions and providing feedback and evaluation to participants