## Sheet1
Financial Proposal for Individual Consultancy: Identification of the profile of children, adolescents and youth who are out-of-school
Applicant name
Address
Contact info
Date
Offer validity (days)
Consultancy
Deliverable (and corresponding activity) | Number of working days | Consultancy fee (daily rate, MDL) | Sub- total
Inception report including Workplan consulted and agreed with UNICEF | 3 |  | 0
Methodology for research on profiles of OOSC, including definitions of OOSC, drop-out, risk of drop-out, early school leaving etc. | 3 |  | 0
Report on the profile of children and adolescents out of school, who are at risk of drop-out or drop-out and those who leave the school early including bottlenecks for their participation and recommendations for improved collection, flow and monitoring of data on children out of school, at risk of dropout, those who drop-out or leave school early. | 15 |  | 0
Methodology of the analysis, including key indicators, data collection tools, instruments and informational flows | 4 |  | 0
Report on the analysis of official education statistics of NBS and administrative data from MECR/EMIS and recommendations to improve data collection on OOSC, absenteeism, drop-out and early school leaving and address existing discrepancies | 10 |  | 0
Methodology at the school, community and national levels for the identification of children at risk of non-returning to school after the COVID-19 pandemic or summer vacation, out of school children and adolescents, early school leavers and those at risk of dropping out of school | 10 |  | 0
Revised MECR instruction on prevention and addressing early school leaving, absenteeism and drop-out in general education | 3 |  | 0
Model of an ‘early warning system’ | 3 |  | 0
Methodology and guidance on how to assess dropouts in schools with identification of groups dropping out, as well as the barriers that prevent them from attending, returning to school or transitioning at the next level | 3 |  | 0
Proposal of low-cost, sustainable school and community-based interventions for children at risk of drop-out or early school leaving in order to reduce drop-out and early school leaving | 2 |  | 0
Draft of an improved monitoring system for children and adolescents out of school and those at risk of non-returning to school, dropping out or of leaving school early with definitions, indicators and benchmarks | 5 |  | 0
Final draft Action plan to address the issue of OOSC, absenteeism, school drop-out and early school leaving, including monitoring and data component | 10 |  | 0
Sub-total Consultancy fee | 71 |  | 0
Other costs ( if relevant)
Type of expenditures ( e.g translation ) (and corresponding activity) | Unit ( daily, hours , page etc.) | Unit cost, MDL per day, hour, page etc. | Sub-total
logistics linked to meetings organization) |  |  | 0
local transportation |  |  | 0
Other (if applicable, please add more lines and specify details in brackets ) |  |  | 0
Sub-total Other costs | X | X | 0
Total, MDL, financial proposal |  |  | 0