## Price Quotation.
NB: The proposed all-inclusive fee should include Professional fee, cost for round trip international travel, cost for in-country travel, Daily Subsistence Allowance (DSA) etc.
Work Assignments Overview | Deliverables/Outputs | Delivery deadline | Proposed Estimated Budget (USD)
Preparatory work | Submission of an approved Inception report, including an adapted and annotated outline of CLAC document and desk review. The report will include a list of proposed meeting partners and resource persons | 12th August 2024
Write Climate Landscape Analysis for Children (CLAC) | Submission of draft CLAC analytical document following KIIs and field visits in Ghana (with meeting notes shared) | 6th September 2024
| Submission of draft roadmap with recommendations and options for prioritization within internal GCO programming and for external engagement | 26th September 2024
Facilitation of internal meetings, and workshops for capacity building and/or consensus building as needed |  | 30th September 2024
Facilitation of external meetings/roundtables, presentations, and validation workshop |  | 6th October 2024
Submission of approved final report (with formatting and an accompanied PowerPoint presentation), including validated recommendations in a prioritized list |  | 13th October 2024
Cost for International Travel
Cost for in-country Travel (6-8 days)
Total all-inclusive fee
Kindly note that the expected content and quality of each deliverable will be elaborated and discussed with the selected consultant in advance. Payment will be based on agreed deliverables/expectations being met.

## Expected deliverables
Expected Deliverables
Scope of Work:
UNICEF in Ghana is planning to conduct a Climate Landscape Analysis for Children (CLAC), as a Foundational Element of the Sustainability and Climate Change Action (SCAP), to examine the baseline situation of CEED issues affecting children in the country, and how they relate to UNICEF’s priorities. The report will explore government policies and strategies, trends, key interventions, financing options and stakeholders. It will also provide detailed, sector-specific recommendations on how UNICEF in Ghana could further incorporate and strengthen its work on CEED issues in its country programme, laying the foundations for a country-level SCAP Action Plan. Also, findings presented in this report will be used for advocacy and support youth engagement, to strengthen investment in relevant sectors to increase children’s access to quality, inclusive, and climate-resilient infrastructure, and to services that ensure they learn in safe and healthy environments; and are protected from WASH-related diseases, as well as from CEED-related forms of exploitation, neglect, and abuse.
Purpose/Objective:
The consultant will lead the production of the Climate Landscape Analysis for Children (CLAC) report, including direction and support to UNICEF in Ghana to programme the recommendations formulated in the CLAC, laying the foundations for a country-level SCAP Action Plan.
Specifically, the consultant will:
1. Collect, compile, and review key resources, including web-based and in-country information, and undertake a stakeholder analysis.
2. Conduct consultation meetings with key stakeholders at national and local level, including government Ministries, local authorities, children, and young people, among others.
3. Analyse the data collected through the desk review, the consultation meetings and field visits, and write the CLAC on the model of CLACs from other countries.
4. Work closely with UNICEF in Ghana’s management and technical staff in relevant sections to identify and develop programming options and recommendations for successfully integrating CEED issues in UNICEF’s country programme cycle in Ghana, for the period 2023-2027.
5. Identify potential innovative financing options (climate or green finance, green procurement, green bonds, etc) for CEED interventions in Ghana.
6. Organize a validation workshop with key stakeholders, in collaboration with the GCO.
Expected Results:
1) Write a Climate Landscape Analysis for Children (CLAC) report
• Adapted outline of the generic template for the CLAC reports developed, tailored to UNICEF’s needs in Ghana:
- Review example reports from other country offices and the global guidance materials.
- Propose any changes needed to accommodate the national context and CO priorities.
• Conduct a desk review and provide an overview of the climate, environment, energy, and disaster risk reduction (CEED) baseline
- Conduct a desk review of the CEED issues, stakeholders and CEED policies, strategies, and key interventions in the country.
- Provide a synthesis of the above, and general implications for the country’s climate resilience and sustainable development agenda, with a focus on issues related to UNICEF’s mandate.
- Review UNICEF’s corporate priorities to assess child rights and CEED linkages.
- Identify knowledge and information gaps.
- Collect, incorporate, and triangulate comments from all stakeholders with reference materials from the desk review.
- Provide an overview of the child rights-CEED nexus in Ghana, including analysis of implications for UNICEF sectors (i.e., health, nutrition, WASH, education, child protection, social policy, gender, social protection, youth and emergency response).
- Identify CEED interventions relevant to UNICEF’s programming in Ghana, including risks to current programming.
- Identify partnership and funding opportunities to support UNICEF’s CEED-related programming in Ghana, including climate finance.
• Conduct interviews & meetings with key stakeholders in the area of CEED and child rights
- Conduct interviews with UNICEF sections, external partners, and stakeholders (i.e., government Ministries, youth groups, academia CSOs, development partners, and the private sector, etc.) on CEED issues affecting children, given complementing and triangulating the information compiled as part of the desk review.
2) Identify priority entry points for UNICEF engagement and CEED programming
• In close collaboration with country office staff, identify and evaluate potential entry points for UNICEF engagement in CEED-related issues
- With UNICEF’s technical staff and Management in Ghana, develop and define priority areas for UNICEF engagement in Ghana.
- Propose options for prioritization of issues and entry points and facilitate the decision-making process.
- Prepare and present a summary presentation of findings for UNICEF in Ghana and relevant Government, development, and other partners, including young people.
- In coordination with the PME section, support the integration of CEED in UNICEF’s programming cycle in Ghana, laying the foundations for a country-level SCAP Action Plan.
- Assess financing options to support CEED evaluating climate and green finance options, green bonds, and green energy.