**International Consultant- Child Rights Monitoring**

**Consultants are expected to provide their financial Proposals (an all-inclusive fee) based on the deliverables outlined in the below table.**

**This should comprise an all-inclusive fee, such as a professional fee, travel costs, etc.**

|  |  |  |  |
| --- | --- | --- | --- |
| Work Assignments Overview | Deliverables/Outputs | Delivery deadline | Estimated Budget |
| 1.To support development and dialogue on MICS MoU with GSSTechnical support to NDPC and GSS on data system interoperability | Detailed work plan of the Consultancy.Final MICS Steering Committee MoU developedDetailed activity plan discussions and plan developed on NDPC and GSS support | 25th January 2024 |  |
| 2. Finalization of MICS Survey guidelines and ongoing support on resource mobilization and MICS partnershipsTechnical support to NDPC and GSS on data system interoperability | Survey guidelines developedActivity report on NDPC and GSS -including meeting minutes. | 20th February 2024 |  |
| 3. Development of SITAN Conference concept note and engagement plan and implementation | Concept Note developed (general one)Policy Note draft of Ghana’s Child Specific SDG developed based on Global report. | 15th March 2024 |  |
| 4. External engagements for Sitan ConferenceSupport the development of Session specific Thematic Concept Notes (CNs) | 2 external engagements held, and reports written2 thematic CNs finalised (SITAN conference thematic sessions) | 20th April 2024 |  |
| 5.External engagements for Sitan Conference Support the development of session specific thematic Concept Notes | 3 external engagements held and reports written3 thematic CNs finalised (SITAN conference thematic sessions) | 25th May 2024 |  |
| 6. SITAN Conference and reporting | SITAN conference report developed | 20th June 2024 |  |
| 7. Child Specific SDG Policy Note -final Coordination of the final validation meeting | Policy Note finalised | 8th July |  |
| 8. NaMEIS technical support to NDPC and GSSMICS training coordinationSupport organization of a capacity building training focused on CRC monitoring and DCAF data quality strengthening to GSS and NDPC | Activity report and Concept Note of GSS and NDPC training. | 10th August 2024 |  |
| 9. MICS Steering group meeting coordination DCAF data quality strengthening to GSS and NDPC | Steering Group report | 15th September 2024 |  |
| 10. Technical support to MICS data collection DCAF data quality strengthening to GSS and NDPC | Midline Activity report of technical support NDPC and GSS support, including lessons learned. | 10th October 2024 |  |
| 11. Technical support to MICS data collection DCAF data quality strengthening to GSS and NDPC GSS DP coordination meeting preparation and secretariat. | GSS DP meeting coordinated and organised, DP meeting report | 15thth November 2024 |  |
| 12. Technical support to GSS and NDPC of NaMEISDCAF data quality strengthening to GSS and NDPC | Final Activity report | 20th December 2024 |  |