|  |  |
| --- | --- |
| ***Section A*** |  |
| Title: | **Nutrition and child development Consultant** (with focus on Nutrition and child Development through ECD Community centers, nurseries, schools, and maternal nutrition)  |

***Section B***

|  |
| --- |
| **Work Assignment Expected Results** |
| Deliverables/Outputs:  | Tasks/Milestone: | Timeline | Percentage of Payment  |
| **Roll out of the school nutrition and meal assessment in partnership with MEHE, WFP and MOPH** | 1. The draft Concept Note is finalized and reviewed from technical perspective
2. The template for agreement with WFP developed based on the Concept Note
3. The Training of field team for the assessment is completed (report of training submitted)
 | March 31st 2024 | 10% |
| 1. Conduct field monitoring during data collection and submission of field visit updates
2. Data collection is completed
 | May 31st 2024 | 10 % |
| 1. Draft report of the assessment is reviewed and submitted for review of all relevant sections
2. UNICEF Inputs are consolidated, and the report is finalized
 | June 30th 2024 | 10 % |
| **Promotion of nutrition behaviours and school nutrition environment** | 1. Development and finalization of four-cycle specific nutrition modules for (pre-school, Cycle 1-2-3) (in coordination with MEHE, WFP and relevant sections)
 | Aug 31st 2024 | 10% |
| 1. Roll out of training plan for health supervisors of public schools – Training plan- training materials.
 | Oct 31st 2024 | 10 % |
| 1. Support in the development and implementation of a national awareness campaign on the food environment and childhood obesity.
2. Coordination and provide technical support to MOPH and MEHE to upgrade existing school nutrition standards and regulations and support undertaking of relevant trainings and meetings
 | Dec 31 2024 | 10% |
| **Adolescent girls and maternal Nutrition** | 1. Support MOPH in scaling up and strengthening maternal nutrition counseling as part of Antenatal Care (ANC) services at the facility level
2. Undertake training sessions for healthcare professionals, and revise guidelines, tools, and Standard Operating Procedures (SOPs) to align with best practices- Training materials and guidelines for the scale-up of maternal nutrition counseling as part of ANC services
 | March 31st 2025 | 10 % |
| **Early Childhood Development, capacity developments and coordination** | 1. 12 bi-monthly internal ECD coronation meetings are supported and organized with minutes submitted
2. At least 5 ECD papers, guideline, proposals, and documents are reviewed/ developed revised
3. Coordinating two office efforts on use of digital for ECD and Nutrition resulting (tools are developed and in place)
4. Coordinating, organizing and as needed facilitating training for young people as part of Vocational training for youth
 | June 30th 2025 | 10% |
| **Universal Salt Iodization** | 1. Supervising the development of the national SOP on Quality Assurance and Quality Control of Salt Iodization for MOET /MOPH and salt producers in Lebanon
2. Coordinating the periodic QA/QC visit of the three salt producers
3. Coordinating the training of national and sub-national labs of MOET and MOPH on SOPs
 | Aug 31st 2025 | 10 % |
| **Food Systems for child nutrition: Food marketing for children**  | 1. Supervise undertaking of food and nutrition environment assessment with focus on food marketing targeting children in multiple platforms (Media, retail, etc.)
2. Support and coordinate development of a SBC campaign on promoting healthy nutrition customer behavior around the food purchased for/by children
3. Supporting MOET to develop needed regulatory frameworks and or legislation/decrees aiming at regulating/controlling the marketing of unhealthy foods for children
4. Coordinate training on child right approach and principles in marketing of food for children
5. At least two child nutrition sensitive food system based income generation activities to incentivize production of nutrition food are coordinated with YAD section and documented
 | Dec 31st 2025 | 10 % |